## Sheet1
Online Movie Ticket Booking System
Company- LTTS
Lead by- Aniket Nagpure
Task | Start Date | Days to complete
Requirement specification and Analysis | 2022-03-19 | 1
Design | 2022-03-20 | 1
Test Cases | 2022-03-21 | 2
Coding with unit testing | 2022-03-22 | 4
Testing | 2022-03-28 | 4
Documentation | 2022-03-31 | 1